## Sheet1
Punch No | Zone | DECK No. | Zone-Punch Number | Action Description | S3D Item Tags | Punched by | Punch Snapshot | Punch Snapshot 2 | Punch Snapshot 3 | Punch Snapshot 4 | Close-Out Snapshot 1 | Close-Out Snapshot 2 | Action Comment | Vendor Discipline | Company | Action by | Status | Date Cleared by KBR | Days Since Date Cleared by KBR | Petrobras Response | Petrobras Response by | Petrobras Response Date | Petrobras Screenshot | Remarks | Petrobras Discipline | Petrobras Category | Date Cleared by Petrobras | Seatrium Remarks | Seatrium Discipline | Checked By (Seatrium) | Seatrium Comments | Date Cleared By Seatrium | Days Since Date Cleared by Seatrium | Modified By | Item Type | Path
0001 | FWMOD | LEVEL 4 |  | Re-route the First pass high pressure pump skid drain pipe to optimise the maintenance space for filter removal. | UD-5122002A/B | PB-Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[3e86278c7f2648fbae8324b20b6bbd0a][1]_[2].png","originalImageName":"0001A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[09f1767d194b483d8e60611f5543474c][1]_[4].png","originalImageName":"0001B"} |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[25b557b161de413fbe34571d15526731][1]_[9].png","originalImageName":"0001a"} | {"fileName":"Reserved_ImageAttachment_[24]_[Close-OutSnapshot2][32]_[816839966a994ace985faf91fdeba50f][2]_[11].png","originalImageName":"0001b"} | Hitachi: Re-route the First pass high pressure pump skid drain pipe to optimise the maintenance space for filter removal. KBR: Noted and Subject to PB Approval | PIP | HAQT | KBR piping | Pending PB Reply | 16/11/2025 | 7.00000000000000 | [6 empty] | Engineering/Technical |  |  | Mechanical | ID: 206 |  | 23/11/2025 | 2.00000000000000 | ID: 206
0002 | FWMOD | LEVEL 4 |  | Relocate the manual valve slightly left side to optimise the access of y-strainer in Biocide dosing system | UD-5122002A/B | PB-Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[fa5bb05714414a6dbddff6e332d56ba0][1]_[2].png","originalImageName":"0002A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[189f8472e2b7494aa832bef9dfdfb67e][1]_[4].png","originalImageName":"0002B"} |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[b9813a9f916d4f49801893bdd2792ffd][1]_[9].png","originalImageName":"0002a"} | {"fileName":"Reserved_ImageAttachment_[24]_[Close-OutSnapshot2][32]_[859256f474164800835e2a36b9fd3f6d][2]_[11].png","originalImageName":"0002b"} | Hitachi: Relocate the manual valve slightly left side to optimise the access of y-strainer in Biocide dosing system. KBR: Noted and Subject to PB Approval. | PIP | HAQT | KBR piping | Pending PB Reply | 16/11/2025 | 7.00000000000000 | [6 empty] | Engineering/Technical |  |  | Mechanical | ID: 206 |  | 23/11/2025 | 2.00000000000000 | ID: 206
0003 | FWMOD | LEVEL 4 |  | Propose to rotate the drain valves to change y-strainer removal orientation | UD-5122002A/B | PB-Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[89fe2c99d1814b7c8853a18d821c6d6a][1]_[2].png","originalImageName":"0003"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[e67cb1af3843469baa1e3889ea07459b][1]_[7].png","originalImageName":"0003a"} |  | Hitachi: Rotate the drain valves to change y-strainer removal orientation. KBR: Noted and Subject to PB Approval | PIP | HAQT | KBR piping | Pending PB Reply | 16/11/2025 | 7.00000000000000 | [6 empty] | Engineering/Technical |  |  | Mechanical | ID: 206 |  | 23/11/2025 | 2.00000000000000 | ID: 206
0004 | FWMOD | LEVEL 4 |  | Rotate the NaOH Y-strainer outward to optimize the accessibility | UD-5122002A/B | PB-Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[4c77d84cb1974ee3aa5e82962999e41c][1]_[2].png","originalImageName":"0004"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[3d989fea7c60458a82245ef279cd8b2c][1]_[7].png","originalImageName":"0004a"} | {"fileName":"Reserved_ImageAttachment_[24]_[Close-OutSnapshot2][32]_[d7e89f25e15b41d7ab02fca6ac030bc1][1]_[9].png","originalImageName":"0004b"} | Hitachi: Rotate the NaOH Y-strainer outward to optimize the accessibility. KBR: Noted and Subject to PB Approval | PIP | HAQT | KBR piping | Pending PB Reply | 16/11/2025 | 7.00000000000000 | [6 empty] | Engineering/Technical |  |  | Mechanical | ID: 206 |  | 23/11/2025 | 2.00000000000000 | ID: 206
0005 | FWMOD | LEVEL 4 |  | Pipe support is blocking the removal access of FIT-5122928A/B. Propose to shift the pipe support to slightly left side or can consider moving the hole penetration if needed | UD-5122002A/B | PB-Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[19dc9110972b4d448ee598934e1b7b0a][1]_[2].png","originalImageName":"0005"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[cd688c3cb32744eabe19a1d511210b2f][1]_[7].png","originalImageName":"0005a"} |  | Hitachi: Shift the pipe support to slightly left side. KBR: Noted and Subject to PB Approval. | PIP | HAQT | KBR piping | Pending PB Reply | 16/11/2025 | 7.00000000000000 | [6 empty] | Engineering/Technical |  |  | Mechanical | ID: 206 |  | 23/11/2025 | 2.00000000000000 | ID: 206
0006 | FWMOD | LEVEL 4 |  | Difficult to access this valve from access way. Optimise the valve accessibility. | UD-5122002A/B | PB-Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[d948c14ac05d479dabd1be8ae4a68d0d][1]_[2].png","originalImageName":"0006A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[c111b5d99e524651a0081eb443ffe946][1]_[4].png","originalImageName":"0006B"} |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[0970ee036dc64a07a01c172cb28a30ef][1]_[9].png","originalImageName":"0006a"} | {"fileName":"Reserved_ImageAttachment_[24]_[Close-OutSnapshot2][32]_[b50aeddbaabd4ea1b8f7a694a0d0d025][2]_[11].png","originalImageName":"0006b"} | Hitachi: Rotate the valve orientation to optimise accessibility. KBR: Noted and Subject to PB Approval. | PIP | HAQT | KBR piping | Pending PB Reply | 16/11/2025 | 7.00000000000000 | [6 empty] | Engineering/Technical |  |  | Mechanical | ID: 206 |  | 23/11/2025 | 2.00000000000000 | ID: 206
0007 | FWMOD | LEVEL 4 |  | Move the PSV pipe manifold upward to prevent the PSV flange from being blocked by the manual valve in front of it, ensuring sufficient space for removal. | UD-5122002A/B | PB-Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[7a5aca7010e94a5a8b86dd3d7cc3d0c2][1]_[2].png","originalImageName":"0007A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[4e70cbd1fe404c9bb414d198dfdd0e67][1]_[4].png","originalImageName":"0007B"} |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[cf1a869f364b4c3f8b62c88c530c09b1][1]_[9].png","originalImageName":"0007a"} | {"fileName":"Reserved_ImageAttachment_[24]_[Close-OutSnapshot2][32]_[6c34e0a4668c44a6a4a9179ee11b8b09][2]_[11].png","originalImageName":"0007b"} | Hitachi: Move up PSV pipe manifold to optimise maintenance space. KBR: Noted and Subject to PB Approval. | PIP | HAQT | KBR piping | Pending PB Reply | 16/11/2025 | 7.00000000000000 | [6 empty] | Engineering/Technical |  |  | Mechanical | ID: 206 |  | 23/11/2025 | 2.00000000000000 | ID: 206
0008 | FWMOD | LEVEL 4 |  | Relocate the calibration column inlet isolation valves to optimise the access of y-strainers in SBS, ATS, and NaOH dosing systems. | UD-5122002A/B | PB-Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[f1b9d71cafe2487d857454db5fa83cc7][1]_[2].png","originalImageName":"0008"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[9a3d0d119e0b4dadbed0a87b4371965c][1]_[7].png","originalImageName":"0008a"} |  | Hitachi: The isolation valves are shifted slightly to left side from the Y-strainer. KBR: Noted and Subject to PB Approval. | PIP | HAQT | KBR piping | Pending PB Reply | 16/11/2025 | 7.00000000000000 | [6 empty] | Engineering/Technical |  |  | Mechanical | ID: 206 |  | 23/11/2025 | 2.00000000000000 | ID: 206
0009 | RGC |  |  | Sundyne to provide 3 stools (only two represented in 3D model) | General | Seatrium / Kenny | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[51c03ad6f0294ac4815123df6a401032][1]_[3].png","originalImageName":"0009"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[5afbae32858d4d4eb1385c8c93d57548][1]_[7].png","originalImageName":"RGC-0009-1"} |  | The additional stool has been implemented. Total there are 3 stools. | Accesibility | Sundyne | SUNDYNE | Pending Seatrium Reply | [8 empty] | Engineering/Technical |  |  | Accessibility |  |  |  |  | ID: 897
0010 | RGC |  |  | Sundyne to update Main motor 3D model with correct position of Terminal box | General | KBR / Karan | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[76dc7d778a174a768f9aee903bd49cb8][1]_[3].png","originalImageName":"0010"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[9f8b6bc3121042428dc0459a281b1234][1]_[7].png","originalImageName":"RGC-0010-1"} | {"fileName":"Reserved_ImageAttachment_[24]_[Close-OutSnapshot2][32]_[cdcbf5ee80794eb3b67f6b38f651e414][1]_[9].png","originalImageName":"RGC-0010-2"} | The updated WEG motor 3D model has been implemented. | Accesibility | Sundyne | SUNDYNE | Pending Seatrium Reply | [8 empty] | Engineering/Technical |  |  | Accessibility |  |  |  |  | ID: 897
0011 | RGC |  |  | Sundyne to move Tie In point for instrument wiring. KBR to inform about position | Instrument | KBR / Roberto | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[88bd8ad1f5164bf4829c29125f68c4c6][1]_[3].png","originalImageName":"0011"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[59d81c6ccf034c95b8254a22c982d78a][1]_[7].png","originalImageName":"RGC-0011-1"} |  | The Instrument Cable tray tie-in and Electrical Cable tray tie-in as shown in the close out snapshot has been reviewed, clarified and agreed with KBR Instrument, KBR Electrical and Sundyne. | Accesibility | Sundyne | SUNDYNE | Pending Seatrium Reply | [8 empty] | Engineering/Technical |  |  | Safety |  |  |  |  | ID: 897
0012 | RGC |  |  | Sundyne to check if Drain valves on the lube oil plate exchanger can be relocated for better accessibility | General | Petrobras / Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[5de6d7d4f00248af8a22533a47dc4cac][1]_[3].png","originalImageName":"0012"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[d7957266f018429c80800dcf8497a56a][1]_[7].png","originalImageName":"RGC-0012-1"} |  | Valves position was relocated to the accessible point inside compressor package. | Maintenance | Sundyne | SUNDYNE | Pending Seatrium Reply | [8 empty] | Engineering/Technical |  |  | Maintenance |  |  |  |  | ID: 897
0013 | RGC |  |  | Sundyne to relocate drain valve of lube oil filter to improve accessibility | General | Petrobras / Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[c468549656e94f1eb1ca2427cd5799b0][1]_[3].png","originalImageName":"0013"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[33eb7a0d3d19436f862dae97e0e2bde6][1]_[7].png","originalImageName":"RGC-0013-1"} |  | Valve position was relocated to the accessible point inside compressor package. | Accesibility | Sundyne | SUNDYNE | Pending Seatrium Reply | [8 empty] | Engineering/Technical |  |  | Accessibility |  |  |  |  | ID: 897
0014 | RGC |  |  | Sundyne to explain how to remove Lube oil motor from lube pump | General | KBR / Karan | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[9201132794f245ad99ce15e8e6a5fa6e][1]_[3].png","originalImageName":"0014"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[cb1c93f981bd499f94434ce71998864b][1]_[7].png","originalImageName":"RGC-0014-1"} |  | For pump maintenance, according to Sundyne sub-supplier, first motor to be removed. Then pump (including plate) can be extracted and removed from oil reservoir. Coupling is jaw type coupling. Supplier will provide details procedure. It will be included in document. | Maintenance | Sundyne | SUNDYNE | Pending Seatrium Reply | [8 empty] | Engineering/Technical |  |  | Maintenance |  |  |  |  | ID: 897
0015 | RGC |  |  | Sundyne to optimize drain valve position of the Seal System | General | Petrobras / Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[3583d03ace5d480c9a249dd6e234af24][1]_[3].png","originalImageName":"0015"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[8c03bcb335454a8a9e898d7d8b7a6fda][1]_[7].png","originalImageName":"RGC-0015"} |  | These lines need to be supported at ends. Sundyne has proposed to reduce the straight length of last spool piece and pull the valve at skid edge. By this way can win appox 50mm from skid edge. | Accesibility | Sundyne | SUNDYNE | Pending Seatrium Reply | [8 empty] | Engineering/Technical |  |  | Accessibility |  |  |  |  | ID: 897
0016 | RGC |  |  | Sundyne to explain how to remove PCV on seal system | General | Petrobras / Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[a2a380af88fa4afca601de96e5ae7a32][1]_[3].png","originalImageName":"0016"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[e192595196d84980854dd2378692bb57][1]_[7].png","originalImageName":"RGC-0016-1"} |  | The tubing routing above this equipment has been updated to allow extraction PCV/ONOFF valve from the top of panel. | Maintenance | Sundyne | SUNDYNE | Pending Seatrium Reply | [8 empty] | Engineering/Technical |  |  | Maintenance |  |  |  |  | ID: 897
0017 | RGC |  |  | Sundyne to rotate lube oil pump discharge pressure transmitters | General | Seatrium / Rasidah | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[17d641f3906d43b79a2369e4009df55c][1]_[3].png","originalImageName":"0017A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[8c679aa0b9eb44d0acefff30b9cd8357][1]_[5].png","originalImageName":"0017B"} |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[d8ea519e045a4ba9becd08526315aa6c][1]_[9].png","originalImageName":"RGC-0017-1"} | {"fileName":"Reserved_ImageAttachment_[24]_[Close-OutSnapshot2][32]_[737d0b31fd9b4b3496d10bda40da2f32][2]_[11].png","originalImageName":"RGC-0017-2"} | Sundyne has proposed to update impulse line tap green (new) vs red (old), refer Close-out snapshot 1. The updated impulse line tap (orange color) will be as shown in Close-out snapshot 2. | Accesibility | Sundyne | SUNDYNE | Pending Seatrium Reply | [8 empty] | Engineering/Technical |  |  | Accessibility |  |  |  |  | ID: 897
0018 | RGC |  |  | Sundyne to try to relocate On Off valve on the walkway edge | General | Petrobras / Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[4f84fbbd13504098b124bbb934486578][1]_[3].png","originalImageName":"0018"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[7613c50f7fc7465b9abe2600acb9b586][1]_[7].png","originalImageName":"RGC-0018-1"} |  | According to Sundyne response, Sundyne is unable to relocate ON OFF valve. However, the tubing routing has been modified allowing extracting ON/OFF valve from the top of panel. | Maintenance | Sundyne | SUNDYNE | Pending Seatrium Reply | [8 empty] | Engineering/Technical |  |  | Maintenance |  |  |  |  | ID: 897
0019 | RGC |  |  | Sundyne to check Seal Gas panel filter elements replacement space | General | Petrobras / Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[1733be9176b64a478507824d529673c5][1]_[3].png","originalImageName":"0019"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[c1eb3bdcae2142828765c228d9b452b1][1]_[7].png","originalImageName":"RGC-0019-1"} | {"fileName":"Reserved_ImageAttachment_[24]_[Close-OutSnapshot2][32]_[2c1b8cdefa0b403990bd2c23e19e6f5e][1]_[9].png","originalImageName":"RGC-0019-2"} | Sundyne confirmed that all filter elements can be removed without clash and all filter elements accessibility are ensured. | Maintenance | Sundyne | SUNDYNE | Pending Seatrium Reply | [8 empty] | Engineering/Technical |  |  | Maintenance |  |  |  |  | ID: 897
0020 | Topside HPU | TANK |  | Vendor to show 3 lighting fixtures in the skid | General | Petrobras-Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[c5f99fed21a24ffcb4f13efab71311cd][1]_[2].png","originalImageName":"0020"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0021 | Topside HPU | ACCUMULATOR |  | Vendor to simulate the removal of the accumulators in the accumulator skid Mirror170-156451_170-15645_53 Mirror170-156451_170-15645_56 170-15645_170-15645_25 170-15645_170-15645_26 170-15645_170-15645_27 | AH-UH-5139001-01 to AH-UH-5139001-27 | Petrobras-Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[4b721d6eb1dc4bf9b9eb65c5b5500683][1]_[2].png","originalImageName":"0021"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0022 | Topside HPU | ACCUMULATOR |  | Vendor to relocate the three accumulators near the removable panel door for both sides. Since the current setup is blocked by a column 170-15645_170-15645_26 Mirror170-156451_170-15645_56 | AH-UH-5139001-01 to AH-UH-5139001-27 | Petrobras-Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[3eba11855c9b4e8e8c9ffc8d8730bf3d][1]_[2].png","originalImageName":"0022"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0023 | Topside HPU | TANK |  | Vendor to model the push button in the ucp panel | PN-UH-5139001 | Petrobras-Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[74fafc208d3b43258fd87b81ab8f5ebb][1]_[2].png","originalImageName":"0023"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0024 | Topside HPU | UCP/HMI |  | Vendor to evaluate the removal of the removable column in front of the UCP panel. Since it impossible to open the UCP panel without removing the column. | PN-UH-5139001 | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[13cf2438ebbb442da6b4b8695e540c82][1]_[2].png","originalImageName":"0024"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0025 | Topside HPU | TANK |  | Vendor to model the space for removing the filters. Vendor to also model the volume/space for removing the filters during maintenance to ensure that there are no clashing or obstructions. | FT-UH-5139001-01A/B/C/D/E ESP-5139001-01A FT-UH-5139001-02A/B | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[87486cc06fb047ca9d9afc2ec525be66][1]_[2].png","originalImageName":"0025"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0026 | Topside HPU | TANK |  | Vendor to model the transfer pump discharge line with the sampling point. Vendor to ensure that the sampling point is to be accessible/ergonomic. | VALV-5139918 & VALV-5139919 | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[31d2b0466f59468281d6c0e2343be58a][1]_[2].png","originalImageName":"0026"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0027 | Topside HPU | TANK |  | Vendor to ensure all the ball valves handle to be rotated to be accessible on top. Vendor to ensure all valve handles are able to operate without any obstructions. | ALL THE VALVES | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[82727fe26b6b4c0ea6c8f637e0a43ed8][1]_[2].png","originalImageName":"0027"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0028 | Topside HPU | TANK |  | Vendor to model all the flexible hose for the suction and discharge line for all the pumps. The current layout is not showing the flexible hoses. | ALL THE PUMPS | Petrobras-Modesto | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[46cbdd1e8d5e404b864f7b7ac493263f][1]_[2].png","originalImageName":"0028"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0029 | Topside HPU | TANK |  | Vendor to relocate the ball valves for the pneumatic suction line and to ensure that the ball valve handles are accessible since current layout is restricted. | VALV-5139835, VALV-5139835A, VALV-5139835B | Petrobras-Daniel | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[67e3f662c510491e831206a5c2ec588b][1]_[2].png","originalImageName":"0029"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0030 | Topside HPU | TANK |  | Vendor to model the four PSV in the discharge line. PSV-5139801-PSV-5139804 To be modelled | PSV-5139801-PSV-5139804 | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[d44dea065e164099838e96ee878fc715][1]_[2].png","originalImageName":"0030A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[da0f9c984c224f54b04d3720c45835e5][1]_[4].png","originalImageName":"0030B"} | [6 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0031 | Topside HPU | TANK |  | Vendor to lower down the PCV in the discharge line. To make it more accesible within operators reach. Since current configuration of the PCV is placed high. | PCV-5139803A & PCV-5139803B | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[474697c4c4cb41b8835d7290127173c1][1]_[2].png","originalImageName":"0031"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0032 | Topside HPU | TANK |  | Vendor to relocate VALV-5139873. To ensure valve operation is not restricted. | VALV-5139873 | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[67c98c05e68c414a8cb10ea68491b24e][1]_[2].png","originalImageName":"0032"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0033 | Topside HPU | TANK |  | Vendor to ensure and model a ladder to access the ball valves. Since the current layout for the ball valves are high. | VALV-5139894 TO VALV-5139900 | Petrobras-Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[a24f72a7935743c588c2d95ab9894cdf][1]_[2].png","originalImageName":"0033"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0034 | Topside HPU | TANK |  | Vendor to model the double block and bleed valve for the accumulator supply line and ensure that all valve handles are accessible. Since current setup is showing only the safety block. | ALL THE ISOLATION BALL VALVES IN THE ACCUMULATOR | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[9d4575c5956c45cca28881b4bd72eea8][1]_[2].png","originalImageName":"0034"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0035 | Topside HPU | TANK |  | Vendor to ensure all the lifting pad eye provided in the skid is provided with SWL. | ALL LIFTING PAD EYE | Petrobras-Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[0753c13736e5404580124507cbae1e84][1]_[2].png","originalImageName":"0035"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0036 | Topside HPU | TANK |  | Vendor to ensure and provide the motor simulation lifting plan for removal during maintenance. Vendor to ensure the axis and the size of the lifting equipment during motor removal. Vendor to model the obstruction volume for motor removal. Current setup only has 89 cm available and the lifting equipment usually takes 60 cm since the remaining space is not sufficient to raise the motor. | M-B-UH-5139001-01A/B | Petrobras-Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[64970c58b5ea40579887f4fd28065372][1]_[2].png","originalImageName":"0036"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0037 | Topside HPU | TANK |  | Vendor to ensure that the motor maker shall confirm to provide 3 points for the motor lifting lugs for vertical lifting. Current motor model is only showing two lifting lugs. | M-B-UH-5139001-01A/B | Petrobras-Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[688c06e6c2a444d38112723d8a835f6d][1]_[2].png","originalImageName":"0037"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0038 | Topside HPU | TANK |  | Vendor to ensure to adjust the location of the temperature transmitter for future maintenance removal. | TIT-5139801 & TIT-5139802 | Petrobras-JULIMAR | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[d3e9e82d57f74b3dab6b82a24c250a49][1]_[2].png","originalImageName":"0038"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0039 | Topside HPU | TANK |  | Vendor to update the hook up drawing and 3D model to show the flushing ring for the removal of the level transmitter. | LIT-5139801 & LIT-5139802 | Petrobras-JULIMAR | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[5ee3de58011b48b184ba4a85ac97ebb7][1]_[2].png","originalImageName":"0039"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0040 | Topside HPU | TANK |  | Vendor to evaluate the usage of floor grating instead of current floor plate setup. Vendor to consider putting grating or non-slip floor plate in order to prevet slippage. | ALL FLOOR PLATE | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[9138e34186f34509835005c6e61df1ac][1]_[2].png","originalImageName":"0040"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0041 | Topside HPU | TANK |  | Vendor to ensure slope of the pump and tank drip pan towards aft to ensure that there is no accumulation of oil | Tank and Pump Drip Pan | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[a568e03e81164be0b1ed31ca2a8303ee][1]_[2].png","originalImageName":"0041"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0042 | Topside HPU | TANK |  | Vendor to ensure to add another drain plug towards the aft for all the drain/drip pans | Accumulator Drip Pan | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[1f421880bf53453ab33cb349667f2404][1]_[2].png","originalImageName":"0042"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0043 | Topside HPU | TANK |  | Vendor to model all ball valves for the drip pan | Tank, Pump, and Accumulator Drip Pan | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[9922696c34f2415f82aaa3894ba993f8][1]_[2].png","originalImageName":"0043"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0044 | Topside HPU | TANK |  | Vendor to consider to remodel the lines so that the ball valves under the motor are reachable by the operator. | VALV-5139832, VALV-5139832A, VALV-5139832B | Petrobras-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[912478969266444e9db44ca66b2b405a][1]_[2].png","originalImageName":"0044"} | [7 empty] | BloomFoss |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0045 | Subsea HPU | TANK |  | Push buttons for pumps to be placed near exit doors. | General | Petrobras/Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[2ac0ad351888472c8d41b5cb9279b499][1]_[4].png","originalImageName":"0045"} | [6 empty] | Safety | JCI |  | OPEN | [8 empty] | Engineering/Technical |  |  | Safety |  |  |  |  | ID: 29
0046 | Subsea HPU | TANK |  | KBR & JCI to demonstrate method of filling reservoir from barrel. | General | Petrobras/Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[fcbee5db78da45dcb0f959766ff8f98f][1]_[2].png","originalImageName":"0046"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0047 | Subsea HPU | TANK |  | Improve access to recirculation pumps (raise height of reservoir if possible & lateral access to be investigated). | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[f80c0db9645b44b4a710a35011cb86a5][1]_[2].png","originalImageName":"0047"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0048 | Subsea HPU | TANK |  | Change pump postions to improve maintenance & accessability, refer to P80 for reference. Possibly above floor, also consider handling. Check external layout/footprint and effects & feasibility. | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[63dfe283a9db4371b8f9700d933e82e5][1]_[2].png","originalImageName":"0048A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[c1ddc363f39849f5bfe01279ef568a7b][1]_[4].png","originalImageName":"0048B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0049 | Subsea HPU | TANK |  | Provide handling plan to show how to remove pumps. To be shown on 3d model | General | Petrobras | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0050 | Subsea HPU | TANK |  | Make reservoir drain valves accessible inside skid | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[53053a06b6be42cc879bb12211ee421a][1]_[2].png","originalImageName":"0050"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0051 | Subsea HPU | TANK |  | Make reservoir and filter sample points accessible for regularr access. Add storage space for fluid particale measurement kit. | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[bd9b366fd85e44f0a44dc3c8c0672f64][1]_[2].png","originalImageName":"0051A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[a0b7d3b9c19c42bd93e89bd0017c574e][1]_[4].png","originalImageName":"0051B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0052 | Subsea HPU | TANK |  | Complete modellling of pipework for recirculation filters. | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[9ecf17f900374c2da1742960565e3585][1]_[2].png","originalImageName":"0052"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0053 | Subsea HPU | TANK |  | LP pump strainers to be added to show accessibility | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[cc754b64da8c4d8d9a7cdf9803eb1f1f][1]_[2].png","originalImageName":"0053"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0054 | Subsea HPU | TANK |  | Isolation valves for electrical and pneumatic pumps to be included in model and to be positoned above floor & made acesssible for maintenance. | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[bcfa155b9eca418c94e44a6662daa4b9][1]_[2].png","originalImageName":"0054"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0055 | Subsea HPU | TANK |  | Accessibility and visibility of pressure transmitters to be improved (In lower position) | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[5fc7562281734de39b3cd16b1b3859cd][1]_[2].png","originalImageName":"0055"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0056 | Subsea HPU | TANK |  | Tube supports to be modelled & shown; spacing and positon to comply with IOGP716. Including how supports are fixed to structure. | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[d5fb09499eef4a3da65d08c13b7ceccc][1]_[2].png","originalImageName":"0056"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0057 | Subsea HPU | TANK |  | Instrument supports and fixing method (brackets) to be modelled. | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[c3b4c397115b41feb1ff60f86f1389fd][1]_[2].png","originalImageName":"0057"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0058 | Subsea HPU | TANK |  | Reservoir level transmitter to be modelled and postion shown on tank. | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[c2440060af7246b18a47bfdfeee2f78b][1]_[2].png","originalImageName":"0058"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0059 | Subsea HPU | TANK |  | Reservoir breather filter access needed to inspect indicator. Move breather to top/side of reservoir (return/right side). JCI to investigate & evaluate technical aspecst or moving breather. Confirm separate compartments of reservoir (supply/return) | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[049c8453a39d41cc97f6e5ac72f33df7][1]_[2].png","originalImageName":"0059A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[f330981e86684bd6a92ad6241a10829f][1]_[4].png","originalImageName":"0059B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0060 | Subsea HPU | TANK |  | Push buttons external to reservoir to be moved to clear access hatch opening range. | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[e005d4c466524c698634b629140c4ad9][1]_[2].png","originalImageName":"0060"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0061 | Subsea HPU | TANK |  | Cover to be added to package push-button (emergency-stop) to avoid accidental operation. Investigate possibility of moving button to outside of panel (covered). | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[7d44589166214118ab712926d8d23577][1]_[2].png","originalImageName":"0061A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[8794afa7c6634c7483122fa9b72621ef][1]_[4].png","originalImageName":"0061B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0062 | Subsea HPU | TANK |  | Removal of some single accumulators is not possible without removal of another accumulator to gain clearance. JCI to provide alternative solutions. | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[3013f1deb00e458aae8062100e4c1478][1]_[2].png","originalImageName":"0062"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0063 | Subsea HPU | TANK |  | Access to accumulator access panels (on top). Steps/ladder necessary to remove fixings &amp; panels. Action TBC | General | Petrobras | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0064 | STGRU | 3 |  | Elevate the handrails on the platform as prevention to follow down. Applicable to both sides. | General | Petrobras - Mateus Rezende Carmona | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[b25ed29e99cf494a9a8bab92028c1819][1]_[1].png","originalImageName":"0064"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0065 | STGRU | 3 |  | Show the escape route 1.0 meter width and walkway area width 800 mm both on 3D model and 2D. Applicable for all elevations. Headroom clearance 2.1 meter. | General | Petrobras - Mateus Rezende Carmona | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[9d82469f79214439afcb2b00744382a1][1]_[1].png","originalImageName":"0065"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0066 | STGRU | 3 |  | Provide the missing handrail and update as per Petrobras standard | General | Petrobras - Mateus Rezende Carmona | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[184cb6b2c46a4107884f71b7f7e621dd][1]_[1].png","originalImageName":"0066"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0067 | STGRU | 3 |  | SDV-1350812 is Category 1 valve and shall be accessible. | SDV-1350812 | Petrobras - Mateus Rezende Carmona | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[84d5ce12734c40b79333b004784806da][1]_[1].png","originalImageName":"0067"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0068 | STGRU | 3 |  | Steps shall be provided to access the ground floor when elevation exceed 300 mm. GARO to discuss with KBR about fixed or portable steps. | General | Petrobras - Mateus Rezende Carmona | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[46668a223b984262a2d5887f8410c328][1]_[1].png","originalImageName":"0068"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0069 | STGRU | 3 |  | Emergency push buttons for the motors to be indicated in the 3D model. Location to be closed to the motors. | General | Petrobras - Mateus Rezende Carmona | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[0eb34f7a54ae4dbfa39402717882d35b][1]_[1].png","originalImageName":"0069"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0070 | STGRU | 3 |  | Fixed platform/steps to be provided in front of the duplex filter to give access to top cover for maintenance and accesso to PG . Elevation fo the platform shall take into account that access to filter valves shall be guaranteed. Show the evelope of the filter internal for maintenance. | General | Petrobras - Mateus Rezende Carmona | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[ddd9ad61f96b4a59b638e1e380bc9b04][1]_[1].png","originalImageName":"0070"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0071 | STGRU | 3 |  | Updated GAD to be provided and shall match with 3D model. (i.e. monorail in GAD not aligned with motor as per 3D model). | General | Petrobras - Juliana | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0072 | STGRU | 3 |  | Garo to consider KBR monorail rest on the above structure. SWL 10 ton. GARO to verify if the structure has any impact. | General | KBR - Kannan | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[fe0c3c866dd642ce98e97146f60eb737][1]_[1].png","originalImageName":"0072"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0073 | STGRU | 3 |  | Handrail on the back of the motors to be removable type in order to allow motor and compressor removal. Garo to check the PB standard about the maximum lenght of removable type handrail. | General | Petrobras - Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[4153735be966495187ef8cc839967b70][1]_[1].png","originalImageName":"0073"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0074 | STGRU | 3 |  | Garo to discuss with KBR and propose a way to handle heavy equipment outside the evelated platform | General | Petrobras - Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[f745d681d3ca4eb7a2335da889d0d280][1]_[1].png","originalImageName":"0074"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0075 | STGRU | 3 |  | Relocate the instrument to an accessible elevation | TIT-1350807B | Petrobras - Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[b0913d91de8a4f16862c9668fc3cc438][1]_[1].png","originalImageName":"0075"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0076 | STGRU | 3 |  | Model all the missing instrument and their support (i.e. PDIT-1350800) | General | Petrobras - Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[245e927298ec485180a0915b76544522][1]_[1].png","originalImageName":"0076"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0077 | STGRU | 3 |  | Relocate valve handwheel 180° | VALV-13508047 | Petrobras - Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[157b7a0fc5fb41f58866a65ac4ba1da0][1]_[1].png","originalImageName":"0077"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0078 | STGRU | 3 |  | Complete the 3D model as per P&ID (i.e. drain lines) | General | Petrobras - Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[17fe3b01853a475db5d2d11d7ab1fb8f][1]_[1].png","originalImageName":"0078"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0079 | STGRU | 3 |  | Garo to fix valves clash with support and valves lever clashes. | General | Petrobras - Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[2ca5be6e96674a95b6968a467b13749d][1]_[1].png","originalImageName":"0079"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0080 | STGRU | 3 |  | Garo to model the compressor drip pans drain and pipe up to battery limit. Drain outletr shall be towards AFT | General | Petrobras - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[a1771a39e3ce46fd8b3b61bd02e66ca2][1]_[1].png","originalImageName":"0080"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0081 | STGRU | 3 |  | Garo to show the ground floor plated with border edge all around. Baseplate drainage system to be implemented. Battery limit and holes to be AFT location. Drainage holes to be provided on corners also. All the holes shall have mesh to avoid any solid to block the drainage system. | General | Petrobras - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[7a8f3d6b041644a48b6b067877e13b3a][1]_[1].png","originalImageName":"0081"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0082 | STGRU | 3 |  | Garo to follow orientation of the PIT, DPIT as per specification (i.e. for liquid service orizontal or 45° down tapping). I-LI-3010.2S-1200-800-S2N-017_B | General | Seatrium - Rasidah | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[da3359e8a55f4aac96759f1fb474e2e4][1]_[1].png","originalImageName":"0082"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0083 | STGRU | 3 |  | Check ergonomics requirement and update. Access | V-UC-1350001-01 | KBR - Piping | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[3944102e98e14e6d9eb3c3fa0e8b1115][1]_[1].png","originalImageName":"0083"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0084 | STGRU | 3 |  | Garo to show all the missing piping support. | General | Petrobras - Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[5348369c27394452b176672188e6d2c1][1]_[1].png","originalImageName":"0084"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0085 | STGRU | 3 |  | Extent the pipe and relocate the instrument to an accessible location | General | Petrobras - Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[066a270eb18e48c4aea747fc4a0177cc][1]_[1].png","originalImageName":"0085"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0086 | STGRU | 3 |  | Drain point for stand pipe is missing. Garo to show | General | Petrobras - Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[ac57c4f841774e5282002da9d2a2d4f4][1]_[1].png","originalImageName":"0086"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0087 | STGRU | 3 |  | Level transmitters capillary type need flushing ring to possible maintenance - I-ET-3010.00-1200-800-PP4X-013 item 6.5..9 | LIT-1350801, LIT-1350803 | Petrobras - Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[3ebf9fdc638b4c27af826065275257c1][1]_[1].png","originalImageName":"0087"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0088 | STGRU | 3 |  | Rotate the globe valves 90° tin order to have handwheel at accessible elevation | General | Petrobras - Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[9cb0793440ae46949e4314afc482306a][1]_[1].png","originalImageName":"0088"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0089 | STGRU | 3 |  | Complete the two instrument air lines with valves and supports | General | Petrobras - Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[f1a2c71f8e5f4c56b509bd42962a458a][1]_[1].png","originalImageName":"0089"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0090 | STGRU | 3 |  | Evaluate the best solution to fill regularly the seal systems. Trolley lifting is not the best solution. | General | Petrobras - Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[829c6a1f10bf48d9bc7bdf42cacd319b][1]_[1].png","originalImageName":"0090"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0091 | STGRU | 3 |  | Gratings openings to have toeplate to avoid any hazard. | General | Petrobras - Saratt | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[483842bd7f274b2a969478423d58a31d][1]_[1].png","originalImageName":"0091"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0092 | STGRU | 3 |  | Handling/Maintenance description for compressors to be submitted for acceptance. Re-evaluate the position of the spectacle blinds for compressor positive isolation | General | Petrobras - Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[d5686d1336714571a5f15a77c8dbd3ed][1]_[1].png","originalImageName":"0092"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0093 | STGRU | 3 |  | Verify the orientation of the T-filter. Shouldn&#39;t be to up? If oriented up evaluate the possibility to lower the gas inlet pipe | ESP-13508011 | Petrobras - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[c97c5d0215d6492bbd25e9db115a55af][1]_[1].png","originalImageName":"0093"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0094 | STGRU | 3 |  | Show the lights and poles and evaluate to install them inside the unit wherever possible | General | Petrobras - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[9054a808dcba484499016a68c4d6c027][1]_[1].png","originalImageName":"0094"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0095 | STGRU | 3 |  | FIT-1350804A/B and 805A/B - Move instruments closer to the process connection | FIT-1350804A/B and 805A/B | Petrobras - Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[5a493de706c7498485d72bda116df794][1]_[1].png","originalImageName":"0095"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0096 | FGRU | 3 |  | Garo to ensure that SWL of the monorail is suitable for the heaviest equipment (i.e. motor). Typical for all three monorails | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[4e51df4e8e7b43fe913b2e8cb0d9ac78][1]_[1].png","originalImageName":"0096"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0097 | FGRU | 3 |  | Garo to show a box with same dimension of the motor at the end of monorail at floor level. | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[e067143ba07746ed90b7281e990f716c][1]_[1].png","originalImageName":"0097"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0098 | FGRU | 3 |  | Provide step above drain pipe for crossover. Two locations | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[5d691e2ab17a45f1a9adb6b3300ddd80][1]_[1].png","originalImageName":"0098"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0099 | FGRU | 3 |  | Evaluate the handling of the three XV valve on the platform above coolers skid | XV-5412812A/B/C | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[1229634303064febacd5f27a111fe0ca][1]_[1].png","originalImageName":"0099"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0100 | FGRU | 3 |  | Garo to check the available space above the filters to allow the removal of the internals. | FT-UC-5412001-01AB | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[8bf12f61cba24245a4efcbe299f2749c][1]_[1].png","originalImageName":"0100"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0101 | FGRU | 3 |  | Ladder details such as fixing to platform, shall be implemnted as per Petrobras standards. Typical for all ladders and handrails. | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[e33513a01d0d4cafbe9b572f2f27b31c][1]_[1].png","originalImageName":"0101"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0102 | FGRU | 3 |  | Garo to evaluate the possibility to connect the two elevated platform to have double access. | General | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[ff11f21360db4271b2ae54fa8e220922][1]_[1].png","originalImageName":"0102"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0103 | FGRU | 3 |  | Show the escape route 1.0 meter width and walkway area width 800 mm both on 3D model and 2D. Applicable for all elevations. Headroom clearance 2.1 meter. | General | Petrobras - Mateus Rezende Carmona | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0104 | FGRU | 3 |  | Emergency push buttons for the motors to be indicated in the 3D model. Location to be closed to the motors. | General | Petrobras - Mateus Rezende Carmona | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[0d094c8ea1d44ad08e714699ffe9d05b][1]_[1].png","originalImageName":"0104"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0105 | FGRU |  |  | Steps shall be provided to access the ground floor when elevation exceed 300 mm. GARO to discuss with KBR about fixed or portable steps. | General | Petrobras - Mateus Rezende Carmona | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0106 | FGRU |  |  | Vendor to consider proper flanged connection on deluge piping to avoid clash during handling of the compressors | General |  | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[371215ee95bd4344a4ce6d9d3665bd97][1]_[1].png","originalImageName":"0106"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0107 | FGRU |  |  | Garo to model the compressor drip pans drain and pipe up to battery limit. Drain outlet shall be towards AFT | General | Petrobras - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[d1d42f12adfc4c4685567caae492ff28][1]_[1].png","originalImageName":"0107"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0108 | FGRU |  |  | Garo to show the ground floor plated with border edge all around. Baseplate drainage system to be implemented. Battery limit and holes to be AFT location. Drainage holes to be provided on corners also. All the holes shall have mesh to avoid any solid to block the drainage system. | General | Petrobras - Mateus | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0109 | FGRU |  |  | Garo to check the plate cooler drain lines. Drains shall be on the lowest process lines. Avoid long small drain line to reduce possible vibration. | P-UC-5412001-01A/B/C | Petrobras - Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[4ae439676d5449f1a755c504d572100c][1]_[1].png","originalImageName":"0109"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0110 | FGRU |  |  | Garo to shown instrument and electrical cable trays. | General | [11 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0111 | FGRU |  |  | Evaluate the instrument height | PIT-5412807A/B/C | Petrobras - Saratt | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[4bd723ce567c46a59543e98b3450dd6e][1]_[1].png","originalImageName":"0111"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0112 | FGRU |  |  | To provide acess (or realocate) the filters PGs. | PG-5412811A/B | Petrobras - Saratt | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[ee973699eeb741e89733c63f841e4e57][1]_[1].png","originalImageName":"0112"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0113 | FGRU |  |  | Level transmitters (diff. pressure) need to be included in the 3D mode | LIT-5412800/801/804/805 | Petrobras - Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[d7450c1ca5834adbbeac294b7d2d893e][1]_[1].png","originalImageName":"0113"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0114 | FGRU |  |  | Provide a vent at the highest point of the gas inlet line | General |  | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[ac2bb3814be64fb2b479f96a6e4d712b][1]_[1].png","originalImageName":"0114"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0115 | FGRU |  |  | Check the T-filter drain route to avoid liquid drain drop on the below vessel | VALV-54128245 | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[bbc8726e314341ecbc08bb442d376264][1]_[1].png","originalImageName":"0115"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0116 | FGRU |  |  | Evaluate drain valve iu/s and d/w LV-5412800 routed downwards or at 45° towards bottom | VALV-54128181 and Valv-54128305 | Petrobras | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[14e0571576954b2a8a40074f8d0a8b03][1]_[1].png","originalImageName":"0116"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0117 | General Notes All Skids | MAYEKAWA |  | Provide a mobile step at the main access points of the skids, as the skid base height exceeds 400 mm. Include a mobile step for access to the skid in the 3D model. |  | PB- Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[f0eeda3c5ad04967b9cd44d9bb7f356c][1]_[2].png","originalImageName":"0117"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0118 | Compressor Skids A/B | MAYEKAWA |  | Provide the access for maintenance of the compressor motor terminal box on both compressor skids. |  | PB - Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[67e5c5f1106d478daee9440fdc240310][1]_[2].png","originalImageName":"0118"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0119 | Compressor Skids A/B | MAYEKAWA |  | Modify the cable tray routing for the heater on both compressors skids. Do not use the path near the floor; implement overhead routing. |  | PB - Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[dfd7a533baf742968c4030564c5e076a][1]_[2].png","originalImageName":"0119"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0120 | Compressor Skids A/B | MAYEKAWA |  | KBR and Mayekawa shall reassess the positioning of the lighting fixtures on both compressor skids. The lighting fixture must be repositioned, as its current location is obstructing the handling of the pressure safety valves, specifically valve tag PSV-1238972A. |  | PB - Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[950b14efdad144f8a431d449c9acfd1c][1]_[2].png","originalImageName":"0120"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0121 | Vessel Skid 2 | MAYEKAWA |  | Add the emergency stop button to the 3D model of Vessel Skid 2. |  | PB - Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[62c400bdea88426da1383c5c697e8fe3][1]_[2].png","originalImageName":"0121"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0122 | Compressor Skids A/B | MAYEKAWA |  | Since the emergency stop button is currently located only on Vessel Skid 2, assess the need to install emergency stop buttons on both compressor skids. |  | PB - Deivisson | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0123 | Vessel Skid 2 | MAYEKAWA |  | Limit the opening angle of the Suction Scrubber manway to 90 degrees in order to avoid clash with the handrail. |  | PB - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[45ac865fab70435da047520e7754236c][1]_[2].png","originalImageName":"0123"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0124 | Vessel Skid 2 | KBR/MAYEKAWA |  | Mayekawa shall verify the possibility of modifying the tie-in point of the PSV in order to enable the operating of the 16” valves installed at the outlet of the Suction Scrubber vessel. |  | KBR | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[6da1eae125634b2b8e0da02879d9d043][1]_[2].png","originalImageName":"0124"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0125 | Vessel Skid 2 | MAYEKAWA |  | Add support structures for instruments LIT-1238901A and LIT-1238902A. |  | PB - Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[1ab57361332545b3a38cbabad845fbb1][1]_[2].png","originalImageName":"0125"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0126 | Vessel Skid 2 | MAYEKAWA |  | Add support structures for instruments LIT-1238901B and 902B |  | PB - Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[68e9871681464077a296b7949340c4b6][1]_[2].png","originalImageName":"0126"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0127 | Vessel Skid 2 | MAYEKAWA |  | Include cable tray to protect the capillary instruments of Suction Scrubber vessel A/B (Z-UT-1238001-02 A/B). |  | PB - Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[285e28b3f3f7450ea984d46143dfb5d3][1]_[2].png","originalImageName":"0127"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0128 | Vessel Skid 2 | MAYEKAWA |  | Correct the insulation thickness of the Suction Scrubber vessels.After updating the insulation thickness, verify the final clearance between the Suction Scrubber vessels. |  | PB - Saratt | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[61a57deab6eb4feeb7d9e6da2f5d5fe8][1]_[2].png","originalImageName":"0128"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0129 | Vessel Skid 2 | MAYEKAWA |  | Model the instruments associated with the Suction Scrubber A/B vessel. ( TW / TE / TIT-1238853A/B and PIT-1238803A/B) |  | PB - Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[a5e43acc7fd9471b9502b01d1daa45a8][1]_[2].png","originalImageName":"0129"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0130 | Vessel Skid 2 | MAYEKAWA |  | Assess the inclusion of a handrail near the instrument assembly of the Suction Scrubber vessel. |  | PB - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[d7cac6765e904694a29b56662d3679f1][1]_[2].png","originalImageName":"0130"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0131 | Vessel Skid 2 | MAYEKAWA |  | Insert the correct valve block and verify the clearance between the valve and the structure to ensure the minimum of the 75mm. |  | PETROBRAS | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[c5023c0ec9774fa88b7342188e8a391b][1]_[2].png","originalImageName":"0131"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0132 | Vessel Skid 2 | MAYEKAWA |  | Insert the correct valve block and improve valve accessibility. |  | PB - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[4276325b0299460d98ed59b23d9c81ab][1]_[2].png","originalImageName":"0132"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0133 | General Notes All Skids | MAYEKAWA |  | Add support structures for all instruments where required or currently missing. |  | PB - Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[25ce2ff4c95343369caa8be8630ade18][1]_[2].png","originalImageName":"0133"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0134 | Vessel Skid 2 | MAYEKAWA |  | Mayekawa to provide drawing and procedure of mobile saddle support. |  | PB - Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[1638a53eb2e54b5b9559409160656307][1]_[2].png","originalImageName":"0134"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0135 | Vessel Skid 2 | KBR |  | KBR to assess and remove clash between lines (3/4"-H-B3-0126-NI and 3/4"-H-B3-0125-NI) and path to revome plate pack from the gas chiller. |  | PB - Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[af281dce10bd4218b91126c33725454c][1]_[2].png","originalImageName":"0135"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0136 | Vessel Skid 1 | MAYEKAWA |  | Correct the 3D model of the collumn in vessel skid 1. |  | PB - Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[fdb266f392f343f3a2b8ee2314b34105][1]_[2].png","originalImageName":"0136"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0137 | Vessel Skid 1 | MAYEKAWA |  | Mayekawa to provide the detail on how to fix the pulling post to the base. |  | PB - Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[b338532f125e450ca737241127f8e1b1][1]_[2].png","originalImageName":"0137"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0138 | Vessel Skid 2 | MAYEKAWA |  | Mayekawa to include the tubing line from oil return pump in the 3D model. |  | KBR - Suresh | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[7729ce24c491420c81c48ca706a7b6ed][1]_[2].png","originalImageName":"0138"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0139 | Vessel Skid 1 | MAYEKAWA |  | Mayekawa to double check if all drain valves have enough space to rotate the handle without clashes with the base or structures and include handle volumes in the 3D model. |  | PB - Mateus | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0140 | Vessel Skid 1 | MAYEKAWA |  | Mayekawa to rotate valve VALV-12388560 to remove clash between handles. |  | PB - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[0e76fc36a25344a7a7305920de730a03][1]_[2].png","originalImageName":"0140"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0141 | Vessel Skid 1 | MAYEKAWA |  | Mayekawa to include in the 3d model the instruments, instrument tubings, instrument rack and cable trays. |  | PB - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[7d5b7286b3f6481db58a7b952cf15f73][1]_[2].png","originalImageName":"0141"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0142 | Vessel Skid 1 | MAYEKAWA |  | Mayekawa to follow the recommended tapping orientation. |  | KBR | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[ffa3b877c5ac43ffb42be4511f771381][1]_[2].png","originalImageName":"0142"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0143 | Vessel Skid 1 | MAYEKAWA |  | Mayekawa to move the column and put and extension to both valves (VALV-12388474 and VALV-12388503) to garantee operation. |  | PB - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[26f4cddb68104e3fb40319059421efea][1]_[2].png","originalImageName":"0143"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0144 | Vessel Skid 1 | MAYEKAWA |  | Mayekawa to check if its possible to locate the skid base drain near to the edge (Aft position). |  | PB - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[5bc1c2726c374d9ea7e8e1286589b41a][1]_[2].png","originalImageName":"0144"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0145 | Vessel Skid 1 | MAYEKAWA |  | On the 3D model, move the spectable blind as per P&ID for the condensers water outlet lines. |  | PB - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[6139133db29648c9afbe45732dc3dddd][1]_[2].png","originalImageName":"0145A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[d52d8c663e454defb64dc0144d5afce0][1]_[7].png","originalImageName":"0145B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0146 | Vessel Skid 1 | MAYEKAWA |  | On the P&ID and 3D model, move the spectable blind for the condensers water inlet lines, because it's between the bypass line. |  | PB - Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[5aaa19853b33473a9ef29b0e58ca5b05][1]_[2].png","originalImageName":"0146A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[ea777f1e04cb42ee89733f49ed2600c2][1]_[4].png","originalImageName":"0146B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0147 | Vessel Skid 1 | KBR/MAYEKAWA |  | Mayekawa and KBR to check if there is enough space to rotate the condenser plate pack. |  | PB - Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[194f9ae5a50d4bdaad7c7083e05f2f08][1]_[2].png","originalImageName":"0147"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 46
0148 | FMS | deck |  | Export gas skid: Flame arrestor to be shipped lose and installed at site by others. Tie-in to face upward, 1" 150#RF flanged connection. |  | KBR | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[3114af107fed4503bf47cc763fb63651][1]_[3].png","originalImageName":"0148"} | [7 empty] | Emerson |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0149 | FMS | deck |  | Export gas skid: Emerson to check and confirm lever of ball valve (VALV-12319924 ) will not clash with nearby items when in CLOSED POSITION. To add model of valve lever in 3d volume. This is applicable to other similar situation. Typical comment for all skids |  | PB (Deivisson) | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[bbc8a24beecd4f77b3026d6ab1059ac0][1]_[2].png","originalImageName":"0149A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[d18e9ad444294cf09c8529f764df30a9][1]_[4].png","originalImageName":"0149B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0150 | FMS | deck |  | Export gas skid: Emerson to model cable trays within the skid. Typical comment for all skids |  | PB (Deivisson) | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0151 | FMS | deck |  | HP fuel gas skid: Emerson to discuss with KBR about alternative method of gas USM (master meter) handling |  | KBR | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[ce19b2bb4ec843afb102c90e57562635][1]_[2].png","originalImageName":"0151"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0152 | FMS | deck |  | HP fuel gas skid: KBR to consider material handling upstream meter tube spools w/ flow conditioner of master meter. Typical for both gas skids. Emerson to indicate dimension and weight of those spools in skid GA's |  | PB (Motter) | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0153 | FMS | deck |  | HP fuel gas skid: Emerson to provide pipe support between 2 inlet bypass valves. Typical for both gas skids |  | PB (Deivisson) | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[40e266e9ce264baabe3aadb64971de4c][1]_[2].png","originalImageName":"0153"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0154 | FMS | deck |  | HP fuel gas skid: Emerson to model temperature transmitter |  | PB (Julimar) | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[c34e778aa6f3469dac047850b56e250b][1]_[2].png","originalImageName":"0154"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0155 | FMS | deck |  | Offloading skid: Emerson to model flush ring with valves at DPT connections near the strainers. To evaluate space for maintenance after modelling. Typical for all diaphragm seal type instrument interface including all strainers. |  | PB (Deivisson) | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[3c2e13d6c8f940cd9f4673784a7a6237][1]_[2].png","originalImageName":"0155"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0156 | FMS | deck |  | Offloading skid: Emerson to relocate PT and stanchion near MV-1359514A/B/C/D |  | PB (Mateus) | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[77d3c1256e6348a1b11cf0b4ef322375][1]_[2].png","originalImageName":"0156"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0157 | FMS | deck |  | Offloading skid: Emerson to model pipe support on small lines |  | PB (Deivisson) | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0158 | FMS | deck |  | Offloading skid: Emerson to ensure mouse holes on beams (for drip pan) to allow flow from FWD to AFT, and slope toward low point. |  | PB (Mateus) | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[2f7cae6930564e7cbdfc49bb7394ea59][1]_[2].png","originalImageName":"0158"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0159 | FMS | deck |  | Fiscal skid: Emerson to reorient 3 JBs facing inward due to structural steel outside the skid. |  | KBR | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[a89587f616a9459caea903b82a7f6ab8][1]_[2].png","originalImageName":"0159"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0160 | FMS | deck |  | Fiscal skid: Emerson to check space in front of strainers for temporary steps needed for maintenance. To model box of 750 x 925 mm for space checking |  | PB (Pamela) | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[9122ae4f56ab4cfbbdde5be7e5bedf89][1]_[2].png","originalImageName":"0160A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[ca61183a44684575af839e5f9ad278e3][1]_[4].png","originalImageName":"0160B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0161 | FMS | deck |  | Fiscal skid: Emerson to ensure mouse holes on beams (for drip pan) to allow flow from FWD to AFT, and slope toward low point. |  | PB (Mateus) | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0162 | FMS | deck |  | Fiscal skid: Emerson to relocate both drip pan nozzles to PORT-AFT side |  | KBR | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[635e7e8de0aa49d5a00f188a8e1368ce][1]_[2].png","originalImageName":"0162"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0163 | FMS | deck |  | Well service skid: Emerson to evaluate access to auto-sampling box. To re-evaluate for other 2 liquid skids |  | PB (Rafael and Pamela) | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[3afcab767e834ad6896eb39aabaa1097][1]_[2].png","originalImageName":"0163"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0164 | FMS | deck |  | Well service skid: Emerson to relocate both drip pan nozzles to PORT-AFT side |  | KBR | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[77102bc976f84a47b0dda78c28a2cd50][1]_[2].png","originalImageName":"0164"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0165 | FMS | deck |  | Well service skid: Emerson to elevate closed drain tie-in by 100 mm |  | KBR | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0166 | SWT |  |  | PB asks to evaluate if it's possible lower calibration pot (citric acid) . Veolia will evaluate if it's possible due are is too tight and equipment is large to accomodate in this area |  | PB / Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[1baa380a06ee48dba71e526162bd8e0f][1]_[2].png","originalImageName":"0166A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[a18119572ba94929a57193a290915d84][1]_[4].png","originalImageName":"0166B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0167 | SWT |  |  | Veolia to evaluate clearance to access y-filters (citric acid pumps) |  | PB / Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[b0c100a5535f4efe8be52c8ecf83c119][1]_[2].png","originalImageName":"0167"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0168 | SWT |  |  | PB asks to Veolia to increase level up to 3000mm vent pipe location from floor |  | PB / Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[df4ff68127984612896d40142742c053][1]_[2].png","originalImageName":"0168"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0169 | SWT |  |  | V eolia to relocate JB /CXE-L-M15-351 and /JBC-1426-800 panels far for front of valve /XV-1251811 |  | PB / Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[acc8460680b0461aaeb68c08157e6106][1]_[2].png","originalImageName":"0169"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0170 | SWT |  |  | Veolia to increase height of /PIT-1251800AtoJ-2 closer to pressure tap point |  | PB / Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[ea6f2f48756d43edab052ef1d57ce1ce][1]_[2].png","originalImageName":"0170"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0171 | SWT |  |  | Veolia to raise sampler point /ESP-12518111 and sample tundish to accomodate between two horizontal bars of guardrail |  | PB / Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[0d7175839bf24021b2d4a36a5d28d9b0][1]_[2].png","originalImageName":"0171"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0172 | SWT |  |  | Veolia to extend grating near the Coarse filter /FT-1251001A/B/C to reduce a gap , applicable for all 03 coarse filters top platform |  | PB / Modesto | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[6a83f9514c804ec5b2901018ef0e790e][1]_[2].png","originalImageName":"0172"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0173 | SWT |  |  | PB asks to raise upper transmitter from 1500mm to 1700mm and bottom transmitter to raise up as much as possible (but keeping below pressure tapping point) , applicable for /INST-FIT-1251800AtoG and /INST-PIT-1251800AtoG-1 |  | PB / Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[2fecff650f25470ea1a337bf88adb89d][1]_[2].png","originalImageName":"0173"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0174 | SWT |  |  | /CXN-L-M15-413 to move box lighting EQUIPMENT 29 of ZONE /P84-SWT-M15-ELEC_LIGHTING-JB_1 |  | PB / Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[520b1bb7b7ed4cc2ae49ee747f228bf4][1]_[2].png","originalImageName":"0174"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0175 | SWT |  |  | PB asks to evaluate if it's possible as much as possible move lightinng fixture from outside, pole type to inside structure; Veolia will evlauate if it's possible whenever is possible or to provide a justification acc. Lighting calculation memory |  | PB / Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[ab60046bcb414fa0a4ee39f27a4bf5b5][1]_[2].png","originalImageName":"0175A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[e5112f5f4f0f469981066df7143e91c9][1]_[4].png","originalImageName":"0175B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0176 | SWT |  |  | Veolia to evaluate /LES-308-UU-M11-007: lighting fixture in the monorail's area of operation |  | PB / Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[f23b0a95770144bd8e1939d8c46852e4][1]_[2].png","originalImageName":"0176"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0177 | SWT |  |  | Veolia to evlauate /PORTABLE-DAVIT: Please provide details on how to fix it to the floor. |  | PB / Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[81d446ded8d548a18b0639bca29eed8b][1]_[2].png","originalImageName":"0177"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0178 | SWT |  |  | PB asks for sectioning handrails in order to provide smaller peace for removable it |  | Seatrium / Kah Mun | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[7ee3c590670e4b04854fab78ed078134][1]_[2].png","originalImageName":"0178"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0179 | SWT |  |  | PB asks to evaluate if it's possible lower calibration pot (citric acid) . Veolia will evaluate if it's possible due are is too tight and equipment is large to accomodate in this area |  | PB / Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[47371ffcd24249c4beabe2a7b93d1565][1]_[2].png","originalImageName":"0179"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0180 | SWT |  |  | Veolia to evaluate clearance to access y-filters (citric acid pumps) |  | PB / Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[3b6220177515460c8327507417bb6ef6][1]_[2].png","originalImageName":"0180"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0181 | SWT |  |  | PB asks to Veolia to increase level up to 3000mm vent pipe location from floor |  | PB / Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[5d501f1fbbc54deb97bf14730716c303][1]_[2].png","originalImageName":"0181"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0182 | SWT |  |  | V eolia to relocate JB /CXE-L-M15-351 and /JBC-1426-800 panels far for front of valve /XV-1251812 |  | PB / Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[b614c653414141459e73954a9c6416ec][1]_[2].png","originalImageName":"0182"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0183 | SWT |  |  | Veolia to increase height of /PIT-1251800AtoJ-2 closer to pressure tap point |  | PB / Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[6c581749b29a4182a1f09a66145bc913][1]_[2].png","originalImageName":"0183"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0184 | SWT |  |  | Veolia to raise sampler point /ESP-12518111 and sample tundish to accomodate between two horizontal bars of guardrail |  | PB / Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[8a7a0f523f0e43628a640605f8dac656][1]_[2].png","originalImageName":"0184"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0185 | SWT |  |  | Veolia to extend grating near the Coarse filter /FT-1251001A/B/C to reduce a gap , applicable for all 03 coarse filters top platform |  | PB / Modesto | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[169c72195d9a4e3498ab4fec9f52bd0e][1]_[2].png","originalImageName":"0185"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0186 | SWT |  |  | PB asks to raise upper transmitter from 1500mm to 1700mm and bottom transmitter to raise up as much as possible (but keeping below pressure tapping point) , applicable for /INST-FIT-1251800AtoG and /INST-PIT-1251800AtoG-2 |  | PB / Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[9fdaa35ddd864282a99cb32bd8beb290][1]_[2].png","originalImageName":"0186"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0187 | SWT |  |  | /CXN-L-M15-413 to move box lighting EQUIPMENT 29 of ZONE /P84-SWT-M15-ELEC_LIGHTING-JB_2 |  | PB / Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[9f594f69997c4bdab8b4ad6207321df9][1]_[2].png","originalImageName":"0187"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0188 | SWT |  |  | PB asks to evaluate if it's possible as much as possible move lightinng fixture from outside, pole type to inside structure; Veolia will evlauate if it's possible whenever is possible or to provide a justification acc. Lighting calculation memory |  | PB / Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[73e9774cee56455ba5a26441b43fcffa][1]_[2].png","originalImageName":"0188"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0189 | SWT |  |  | Veolia to evaluate /LES-308-UU-M11-007: lighting fixture in the monorail's area of operation |  | PB / Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[b7a89b3615524d21b7a9133c4a048b6d][1]_[2].png","originalImageName":"0189A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[23d5b39e7ae64b14b4ee0f1f3a646836][1]_[4].png","originalImageName":"0189B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0190 | SWT |  |  | Veolia to evlauate /PORTABLE-DAVIT: Please provide details on how to fix it to the floor. |  | PB / Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[741ae7573f374b69ae97ed5554bc35bd][1]_[2].png","originalImageName":"0190"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0191 | CIU | LEVEL 2 |  | (All Pump Skids) Tagging for instruments in models. |  | PB-Mateus | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 499
0192 | CIU | LEVEL 2 |  | (PS01-PS04) Calibration pot to be parallel with the stroke adjustor |  | PB-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[0c73244f64224200949ebfedb8a89d97][1]_[4].png","originalImageName":"0192"} | [5 empty] | s explained during the DR90% model review to Petrobras: 1. The stroke adjustment will be done as the first step, and the pump will require to stabilise with new flowrate.. 2. The upstream valve of the calibration pot will be open for calibration pot to be filled as means of gravity. 3. At this instance, the pump will have been stabilised and the pump suction line valve from the tank can be closed. 4. The pump will only withdraw fluid from the calibration pot as the suction line valve have been closed as per Point 4. 5. The operator is only required to be position near the calibration pot to have flowrate reading taken at 60 sec intervals. Therefore, there is no direct correlation of Calibration pot required to be parallel with the stroke adjustor as both activities (To adjust the stoke and read the calibration pot) is considered 2 activities with ample of time in between for operator to position themselves No modification required. KBR : Acceptable subject to PB approval |  |  | LEWA | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 499
0193 | CIU | LEVEL 2 |  | (All Pump Skids) Nameplate to be included. | PB-Pamela | PB-Pamela | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0194 | CIU | LEVEL 2 |  | (All pump skids) Supports to be added for all the instruments. | PB- Julimar | PB- Julimar | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0195 | CIU | LEVEL 2 |  | (PS01-PS04) To check on PDIT isolation valves to be horizontal position and is acessible from internal pltform. | PB-Pamela | PB-Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[7fd4dd9f3a974af280a40d72c40629a1][1]_[2].png","originalImageName":"0195A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[bafa892c9f4f42ccbe3d2ce0381c8da4][1]_[4].png","originalImageName":"0195B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0196 | CIU | LEVEL 2 |  | (PS05) To complete and optimise the design including the pcv line | PB-Deivisson | PB-Deivisson | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[8cae6fcb02214a8bafc29a6432d6fef3][1]_[2].png","originalImageName":"0196A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[41d23f20d1a54379894398668ab7fbc6][1]_[4].png","originalImageName":"0196B"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot3][32]_[a377955e88604f398fa0c7ca7b57b6c1][1]_[6].png","originalImageName":"0196C"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot4][32]_[f0f0130a7d074841ab54fdb4d6dcf5b9][1]_[8].png","originalImageName":"0196D"} | [6 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0197 | CIU | LEVEL 2 |  | (All pump skids) To include the cleat supports for deluge piping | SEA | SEA | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0198 | CIU | LEVEL 2 |  | (PS06) Kickplate to be lowered down for minimum 50mm from the top of the grating to provide access for the suction filter and valves (ESP-12638055 / 12638051) | PB-Pamela | PB-Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[0e8efe7bbf4747faa13d22454493c3d3][1]_[2].png","originalImageName":"0198"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0199 | CIU | LEVEL 2 |  | (PS07) Kickplate to be lowered down for minimum 50mm from the top of the grating to provide access for the suction filter | PB-Pamela | PB-Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[26c4f6092a4b48b898d2202d20c3f4c1][1]_[2].png","originalImageName":"0199A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[df5f8d385d454930a88918844542dbb0][1]_[4].png","originalImageName":"0199B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0200 | CIU | LEVEL 2 |  | (PS07) To relocate and optimise the location of the push start button for easy identification. | PB-Pamela | PB-Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[e84df0f9b4ab4e69ba1e46b014b662c1][1]_[2].png","originalImageName":"0200"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0201 | CIU | LEVEL 2 |  | (PS07) To study the relocation of the push start button as per marked up location. | PB-Pamela | PB-Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[4886a9e3d55d4147bdb4b3129fb435ab][1]_[2].png","originalImageName":"0201A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[f908801dddfe427ca207a97ae26ebe14][1]_[4].png","originalImageName":"0201B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0202 | CIU | LEVEL 2 |  | (PS08) Kickplate to be lowered down for minimum 50mm from the top of the grating to provide access for the suction filter. | PB-Pamela | PB-Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[c72bdc5e4eb94513982860440362339b][1]_[2].png","originalImageName":"0202"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0203 | CIU | LEVEL 2 |  | (PS08) To check and improve the height of instruments and valves. (Lower the instruments, Highest point of valve is 1.9m, transmitter is 1.78m) | PB- Julimar | PB- Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[4c2a3c3a975b4ac0bfded31960801f23][1]_[2].png","originalImageName":"0203"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0204 | CIU | LEVEL 2 |  | (PS08) To ensure the valve is not too near to the structure for valve handling. | PB- Julimar | PB- Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[5ada57bc63f34b428ff2d8e64e5a1db0][1]_[2].png","originalImageName":"0204"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0205 | CIU | LEVEL 2 |  | (PS08) To check and improve (lower down / tilt) the height of instruments (FIT) | PB- Julimar | PB- Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[360f8cc822074d04b62477d43e2e448d][1]_[2].png","originalImageName":"0205"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0206 | CIU | LEVEL 2 |  | (PS08) To check on motor terminal box accessibility. | PB- Julimar | PB- Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[81bc47ac1f31464aaed819e5ead33180][1]_[2].png","originalImageName":"0206"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0207 | CIU | LEVEL 2 |  | (PS08) To include push start button. | PB- Julimar | PB- Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[fe65eb96044e48de92e8512bf7a1a4eb][1]_[2].png","originalImageName":"0207"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0208 | CIU | LEVEL 2 |  | (PS09) To check the accessibility of the motor terminal box | PB- Julimar | PB- Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[cb23f315773c480982f1e0d4b830941a][1]_[2].png","originalImageName":"0208"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0209 | CIU | LEVEL 2 |  | (PS09) To check the staircase/ladder design. PB preferred to have staircase design. | PB- Julimar | PB- Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[18790322c1e64e6fa16be25eaffca36c][1]_[2].png","originalImageName":"0209"} |  |  |  | {"fileName":"Reserved_ImageAttachment_[30]_[Close-Out Snapshot][32]_[a0c1cdc041b64b54bc13158466438d28][1]_[4].png","originalImageName":"0209X"} |  | LEWA have checked and it is seen that the Pump Skid Structural have been fabricated. The Pump Skid to maintain with ladder for access to the platform. Changing as per Model 90% design comment will involve major modifcation and issues with delivery of pump skid to Seatrium. |  |  |  | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0210 | CIU | LEVEL 2 |  | (PS10) Kickplate to be lowered down for minimum 50mm from the top of the grating to provide access for the suction filter. | PB-Pamela | PB-Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[715429b1d4de42edb932e656837d7251][1]_[2].png","originalImageName":"0210"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0211 | CIU | LEVEL 2 |  | (PS10) To add grating on the first step. | PB-Mateus | PB-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[dd86d08d480f42dd8a343d3da8742bfa][1]_[2].png","originalImageName":"0211"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0212 | CIU | LEVEL 2 |  | (PS10) The isolation valve blocks the drain plugs area. | PB-Mateus | PB-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[5f6b4a27e5f943b5a932861c6305722e][1]_[2].png","originalImageName":"0212A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[387cb9cadf3346658067accbf3cbc4dd][1]_[4].png","originalImageName":"0212B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0213 | CIU | LEVEL 2 |  | (PS10) Tubing blocking the push start button. | PB-Mateus | PB-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[150137e0622e47d5bcebd23decd4baea][1]_[2].png","originalImageName":"0213A"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[ea2653fb89e34c1a93a7ce7b4238425e][1]_[4].png","originalImageName":"0213B"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0214 | CIU | LEVEL 2 |  | (PS11) Terminal box to allow for the installation of the cable gland. | PB-Mateus | PB-Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[798abeea84664f4ea2edb88dd11473f9][1]_[2].png","originalImageName":"0214"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0215 | CIU | LEVEL 2 |  | (PS12) To relocate and optimise the location of the push start button for easy identification. | PB-Pamela | PB-Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[b9241bee6bc5488fbe586b7cd762d524][1]_[2].png","originalImageName":"0215"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0216 | CIU | LEVEL 2 |  | (PS12) Kickplate to be lowered down for minimum 50mm from the top of the grating to provide access for the suction filter. (B-UQ-1262001-01A/B) | PB-Pamela | PB-Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[e8668b0942324616a08da7dc55b6a9e8][1]_[2].png","originalImageName":"0216"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0217 | CIU | LEVEL 2 |  | (PS12) To evaluete the space from B-UQ-1261001-04A maintenance, due to the structure behind the equipment. | PB-Pamela | PB-Pamela | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[c769fd96a53b41b38edb2d855f5eee23][1]_[2].png","originalImageName":"0217"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0218 | CIU | LEVEL 3 |  | (All Tanks) To include vent and drain valve on flushing ring of LIT. |  | PB-Julimar | {"type":"thumbnail","fileName":"0218.png","nativeFile":{},"fieldName":"Punch Snapshot","serverUrl":"","fieldId":"128bc15a-3992-4d93-bf3f-aaec5ca36c0b","serverRelativeUrl":"blob:https://seatrium.sharepoint.com/adb37284-17b8-4fd4-b21e-aac1183a4767"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 29
0219 | CIU | TANK |  | Access to accumulator access panels (on top). Steps/ladder necessary to remove fixings &amp; panels. Action TBC | General | Petrobras / Juliana | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[f4228ceb809b4759955117384d9ae3e3][1]_[2].png","originalImageName":"0219"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 19
0220 | CIU | TANK |  | Make ball valves for isolating pumps & strainers (ESP-12101007 / 08 / 17 / 18) easily accessible (eg BV01/7, 8 /9 /10), above floor. | General | Petrobras / Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[a4e2455c4bf5474c8aa9012953c7b98a][1]_[2].png","originalImageName":"0220"} | {"fileName":"Reserved_ImageAttachment_[14]_[PunchSnapshot2][32]_[fd99809a7e2949da95ca7f44f8b86767][1]_[4].png","originalImageName":"0220-1"} | [8 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 19
0221 | CIU | TANK |  | JCI to show outlet lines/tubing, piping and cable tray/runs (currently missing from model) for review by Petrobras. | General | Petrobras / | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 19
0222 | CIU(PUPS) | TANK |  | HV01 (button for pump operation) to be made easily accessible. | General - UH-121002/3 | Petrobras / Mateus | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[7b6b653394594c83adf442563bd856eb][1]_[3].png","originalImageName":"0222"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 19
0223 | CIU(WCR) | TANK |  | Ensure that filters, instruments and valves are easily accessalble as modelling of tubing progresses. | General - PN-1210008 | Petrobras / Mateus | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 19
0224 | CIU(WCR) | TANK |  | Make provision to run tubing vertically down to ground level. Investigate options to adjust TP positions. | General - PN-1210008 | KBR / Budi | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[c2ff275fc0204a62b944b0c4c285991a][1]_[1].png","originalImageName":"0224"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 19
0225 | CIU(WCR) | TANK |  | Make manifold handles easily accesible for operation. | General - PN-1210008 | Petrobras / Julimar | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[71ce11acdd8c431d883d8a5870387223][1]_[1].png","originalImageName":"0225"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 19
0226 | CIU(SESDV) | TANK |  | Make provision to run tubing vertically down to ground level (and clear drain plug) Investigate options to adjust TP positions. | General - PN-1210009 | KBR / Budi | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[5c12053249a848469e9e06a5ce97dbc4][1]_[1].png","originalImageName":"0226"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 19
0227 | CIU(SESDV) | TANK |  | Move both electrical junction boxes to same side of panel (external). | General - PN1210009 | KBR / Budi | {"fileName":"Reserved_ImageAttachment_[20]_[Punch Snapshot][32]_[d0d28e4a81684247b11cdf3c5103e348][1]_[1].png","originalImageName":"0227"} | [9 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 19
0228 | CIU(SESDV) | TANK |  | Ensure that filters, instruments and valves are easily accessalble as modelling of tubing progresses. | General - PN1210009 | Petrobras / Mateus | [10 empty] | OPEN | [8 empty] | Engineering/Technical | [7 empty] | ID: 19